## Summary
Blue Triangle Portal — Comprehensive Automation Testing Plan
QA Automation — US2 (GDC Test Site 2) ¦ Portal: https://portal.bluetriangle.com/ ¦ Plan as of 03-Aug-2026
Metric | Value
Total portal screens in plan | 72
Screens completed | 13
Screens remaining (Planned) | 59
Submodule buffer slots | 12
Automation progress % | 18%
Total planned effort (hours) | 712
Effort completed (hours) | 120
Effort remaining (hours) | 592
Historical cadence | 1 screen / calendar day (22-Jul → 03-Aug)
Forward cadence | 1 screen / business day (Mon–Fri) + submodule buffers
Standard ETA per screen | 8 hours
Plan start (completed work) | 22-Jul-2026
Next screen start | 04-Aug-2026
Projected plan end (incl. buffers) | 17-Nov-2026
Profile / site focus | US2 — GDC Test Site 2
Progress by Module / Submodule (screens only)
Module | Submodule | Completed | Remaining | Buffer Hours (forward)
Monitoring | Real User Browser | 8 | 0 | 0
Business Insights | Improve Conversion | 1 | 8 | 16
Business Insights | Improve Traffic | 4 | 4 | 16
Business Insights | Improve Revenue | 0 | 3 | 4
Monitoring | Advanced Reporting & Alerting | 0 | 6 | 8
Monitoring | Logs | 0 | 7 | 16
Monitoring | Native App | 0 | 5 | 8
Monitoring | Synthetic — Real Browser | 0 | 11 | 24
Monitoring | Synthetic — API Checks (Base Page) | 0 | 3 | 4
Monitoring | Network Health Checks | 0 | 3 | 4
Monitoring | CSP & Tag Governance | 0 | 7 | 16
Account | Account Settings | 0 | 2 | 4
Status color legend
Completed
Planned
Buffer
In Progress
Blocked

## Automation Plan
Sr. No | Module | Submodule | Screen Name | Automation ETA (In hours) | Start Date | End Date | Status | Notes
1 | Monitoring | Real User Browser | Performance Overview | 8 | 22-Jul-2026 | 22-Jul-2026 | Completed | Regression suite delivered; Allure + workbook available.
2 | Monitoring | Real User Browser | Performance Detail | 8 | 23-Jul-2026 | 23-Jul-2026 | Completed | Regression suite delivered; Allure + workbook available.
3 | Monitoring | Real User Browser | Performance Comparison | 8 | 24-Jul-2026 | 24-Jul-2026 | Completed | Regression suite delivered; Allure + workbook available.
4 | Monitoring | Real User Browser | Aggregate Waterfall | 8 | 25-Jul-2026 | 25-Jul-2026 | Completed | Regression suite delivered; Allure + workbook available.
5 | Monitoring | Real User Browser | Bounce & Exit Analysis | 8 | 26-Jul-2026 | 26-Jul-2026 | Completed | Regression suite delivered; Allure + workbook available.
6 | Monitoring | Real User Browser | Errors Explorer | 8 | 27-Jul-2026 | 27-Jul-2026 | Completed | Regression suite delivered; Allure + workbook available.
7 | Monitoring | Real User Browser | Performance Budget | 8 | 28-Jul-2026 | 28-Jul-2026 | Completed | Regression suite delivered; Allure + workbook available.
8 | Monitoring | Real User Browser | Session Lookup | 8 | 29-Jul-2026 | 29-Jul-2026 | Completed | Regression suite delivered; Allure + workbook available.
9 | Business Insights | Improve Conversion | Revenue Opportunity | 8 | 30-Jul-2026 | 30-Jul-2026 | Completed | First BI Improve Conversion screen completed.
10 | Business Insights | Improve Traffic | Marketing Overview | 8 | 31-Jul-2026 | 31-Jul-2026 | Completed | Improve Traffic track started.
11 | Business Insights | Improve Traffic | Core Web Vitals (VitalScope) | 8 | 01-Aug-2026 | 01-Aug-2026 | Completed | Same underlying RUM performance-overview route; covered via BI Improve Traffic path. RUM VitalScope leaf treated as same coverage.
12 | Business Insights | Improve Traffic | Customer Journey Analysis | 8 | 02-Aug-2026 | 02-Aug-2026 | Completed | conversion-type=sales; Brand sibling is separate screen.
13 | Business Insights | Improve Traffic | Brand Customer Journey Analysis | 8 | 03-Aug-2026 | 03-Aug-2026 | Completed | conversion-type=brand; completed 03-Aug-2026 (31/31 passed).
14 | Monitoring | Real User Browser | [Buffer] Bulk regression fix & suite stabilization | 16 | 22-Jul-2026 | 03-Aug-2026 | Completed | Stabilization absorbed across delivery window (defect fixes, Allure isolation, serial soft-deadline hardening). Documented for leadership visibility.
15 | Business Insights | Improve Traffic | My Campaign | 8 | 04-Aug-2026 | 04-Aug-2026 | Planned | Continue Improve Traffic sequence from portal menu order.
16 | Business Insights | Improve Traffic | Competitive Index Table | 8 | 05-Aug-2026 | 05-Aug-2026 | Planned | view=table; pair with Trends screen.
17 | Business Insights | Improve Traffic | Competitive Index Trends | 8 | 06-Aug-2026 | 06-Aug-2026 | Planned | view=trends; pair with Table screen.
18 | Business Insights | Improve Traffic | Bottom of the Sales Funnel Analysis | 8 | 07-Aug-2026 | 07-Aug-2026 | Planned | Last Improve Traffic leaf in current catalog.
19 | Business Insights | Improve Traffic | [Buffer] Improve Traffic — bulk regression run & failure fix | 16 | 10-Aug-2026 | 11-Aug-2026 | Buffer | Reserved after all screens in submodule (total 8: 4 already done + 4 newly scheduled). Run suites in bulk, triage flakes/hard failures, refresh Allure, update workbooks.
20 | Business Insights | Improve Conversion | Dashboards | 8 | 12-Aug-2026 | 12-Aug-2026 | Planned | BI dashboards (exclude marketing=yes My Campaign).
21 | Business Insights | Improve Conversion | Revenue Analysis | 8 | 13-Aug-2026 | 13-Aug-2026 | Planned | conversion-type=sales.
22 | Business Insights | Improve Conversion | Brand Opportunity | 8 | 14-Aug-2026 | 14-Aug-2026 | Planned | Brand conversion sibling of Revenue Opportunity.
23 | Business Insights | Improve Conversion | Brand Analysis | 8 | 17-Aug-2026 | 17-Aug-2026 | Planned | conversion-type=brand.
24 | Business Insights | Improve Conversion | Revenue Calculator | 8 | 18-Aug-2026 | 18-Aug-2026 | Planned | conversion-type=sales.
25 | Business Insights | Improve Conversion | Brand Calculator | 8 | 19-Aug-2026 | 19-Aug-2026 | Planned | conversion-type=brand.
26 | Business Insights | Improve Conversion | Revenue Attribution | 8 | 20-Aug-2026 | 20-Aug-2026 | Planned | Read-only regression; do not mutate attribution config in automation.
27 | Business Insights | Improve Conversion | Brand Attribution | 8 | 21-Aug-2026 | 21-Aug-2026 | Planned | Read-only regression; do not mutate attribution config in automation.
28 | Business Insights | Improve Conversion | [Buffer] Improve Conversion — bulk regression run & failure fix | 16 | 24-Aug-2026 | 25-Aug-2026 | Buffer | Reserved after all screens in submodule (total 9: 1 already done + 8 newly scheduled). Run suites in bulk, triage flakes/hard failures, refresh Allure, update workbooks.
29 | Business Insights | Improve Revenue | Cart Refresh | 8 | 26-Aug-2026 | 26-Aug-2026 | Planned | Broken-links / cart refresh analytics.
30 | Business Insights | Improve Revenue | Out of Stock | 8 | 27-Aug-2026 | 27-Aug-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
31 | Business Insights | Improve Revenue | Revenue Assurance | 8 | 28-Aug-2026 | 28-Aug-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
32 | Business Insights | Improve Revenue | [Buffer] Improve Revenue — bulk regression run & failure fix | 4 | 31-Aug-2026 | 31-Aug-2026 | Buffer | Reserved after all screens in submodule (total 3: 0 already done + 3 newly scheduled). Run suites in bulk, triage flakes/hard failures, refresh Allure, update workbooks.
33 | Monitoring | Advanced Reporting & Alerting | Digital Experience Overview | 8 | 01-Sep-2026 | 01-Sep-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
34 | Monitoring | Advanced Reporting & Alerting | Executive KPI Report | 8 | 02-Sep-2026 | 02-Sep-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
35 | Monitoring | Advanced Reporting & Alerting | CrUX Report | 8 | 03-Sep-2026 | 03-Sep-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
36 | Monitoring | Advanced Reporting & Alerting | Automated Reports | 8 | 04-Sep-2026 | 04-Sep-2026 | Planned | List/view only — exclude create flows.
37 | Monitoring | Advanced Reporting & Alerting | Alerts | 8 | 07-Sep-2026 | 07-Sep-2026 | Planned | List/view only — exclude create flows.
38 | Monitoring | Advanced Reporting & Alerting | Data Science | 8 | 08-Sep-2026 | 08-Sep-2026 | Planned | Custom comparison / data science.
39 | Monitoring | Advanced Reporting & Alerting | [Buffer] Advanced Reporting & Alerting — bulk regression run & failure fix | 8 | 09-Sep-2026 | 09-Sep-2026 | Buffer | Reserved after all screens in submodule (total 6: 0 already done + 6 newly scheduled). Run suites in bulk, triage flakes/hard failures, refresh Allure, update workbooks.
40 | Monitoring | Logs | Alerts Log | 8 | 10-Sep-2026 | 10-Sep-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
41 | Monitoring | Logs | Reports Log | 8 | 11-Sep-2026 | 11-Sep-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
42 | Monitoring | Logs | Domain Violation & Audit Log | 8 | 14-Sep-2026 | 14-Sep-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
43 | Monitoring | Logs | Synthetic Monitors Log | 8 | 15-Sep-2026 | 15-Sep-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
44 | Monitoring | Logs | Instant Measurement Log | 8 | 16-Sep-2026 | 16-Sep-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
45 | Monitoring | Logs | Consultant Access History | 8 | 17-Sep-2026 | 17-Sep-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
46 | Monitoring | Logs | Site Variables Log | 8 | 18-Sep-2026 | 18-Sep-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
47 | Monitoring | Logs | [Buffer] Logs — bulk regression run & failure fix | 16 | 21-Sep-2026 | 22-Sep-2026 | Buffer | Reserved after all screens in submodule (total 7: 0 already done + 7 newly scheduled). Run suites in bulk, triage flakes/hard failures, refresh Allure, update workbooks.
48 | Monitoring | Native App | Performance Overview | 8 | 23-Sep-2026 | 23-Sep-2026 | Planned | Native App overview (distinct from RUM Browser).
49 | Monitoring | Native App | Performance Detail | 8 | 24-Sep-2026 | 24-Sep-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
50 | Monitoring | Native App | Aggregate Waterfall | 8 | 25-Sep-2026 | 25-Sep-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
51 | Monitoring | Native App | Bounce & Exit Analysis | 8 | 28-Sep-2026 | 28-Sep-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
52 | Monitoring | Native App | Errors Explorer | 8 | 29-Sep-2026 | 29-Sep-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
53 | Monitoring | Native App | [Buffer] Native App — bulk regression run & failure fix | 8 | 30-Sep-2026 | 30-Sep-2026 | Buffer | Reserved after all screens in submodule (total 5: 0 already done + 5 newly scheduled). Run suites in bulk, triage flakes/hard failures, refresh Allure, update workbooks.
54 | Monitoring | Synthetic — Real Browser | Performance Overview | 8 | 01-Oct-2026 | 01-Oct-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
55 | Monitoring | Synthetic — Real Browser | Performance Detail | 8 | 02-Oct-2026 | 02-Oct-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
56 | Monitoring | Synthetic — Real Browser | Test Results | 8 | 05-Oct-2026 | 05-Oct-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
57 | Monitoring | Synthetic — Real Browser | Error State Tracking | 8 | 06-Oct-2026 | 06-Oct-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
58 | Monitoring | Synthetic — Real Browser | Page Performance Comparison | 8 | 07-Oct-2026 | 07-Oct-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
59 | Monitoring | Synthetic — Real Browser | Aggregate Waterfall | 8 | 08-Oct-2026 | 08-Oct-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
60 | Monitoring | Synthetic — Real Browser | Errors Explorer | 8 | 09-Oct-2026 | 09-Oct-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
61 | Monitoring | Synthetic — Real Browser | Synthetic Monitors | 8 | 12-Oct-2026 | 12-Oct-2026 | Planned | List/view — avoid create/edit/run write paths.
62 | Monitoring | Synthetic — Real Browser | Erroring Synthetic Monitors | 8 | 13-Oct-2026 | 13-Oct-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
63 | Monitoring | Synthetic — Real Browser | Synthetic Codes | 8 | 14-Oct-2026 | 14-Oct-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
64 | Monitoring | Synthetic — Real Browser | Central Data Repositories | 8 | 15-Oct-2026 | 15-Oct-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
65 | Monitoring | Synthetic — Real Browser | [Buffer] Synthetic — Real Browser — bulk regression run & failure fix | 24 | 16-Oct-2026 | 20-Oct-2026 | Buffer | Reserved after all screens in submodule (total 11: 0 already done + 11 newly scheduled). Run suites in bulk, triage flakes/hard failures, refresh Allure, update workbooks.
66 | Monitoring | Synthetic — API Checks (Base Page) | Performance Overview | 8 | 21-Oct-2026 | 21-Oct-2026 | Planned | Base page overview.
67 | Monitoring | Synthetic — API Checks (Base Page) | Performance Detail | 8 | 22-Oct-2026 | 22-Oct-2026 | Planned | Base page & SSL detail.
68 | Monitoring | Synthetic — API Checks (Base Page) | Test Results | 8 | 23-Oct-2026 | 23-Oct-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
69 | Monitoring | Synthetic — API Checks (Base Page) | [Buffer] Synthetic — API Checks (Base Page) — bulk regression run & failure fix | 4 | 26-Oct-2026 | 26-Oct-2026 | Buffer | Reserved after all screens in submodule (total 3: 0 already done + 3 newly scheduled). Run suites in bulk, triage flakes/hard failures, refresh Allure, update workbooks.
70 | Monitoring | Network Health Checks | Performance Overview | 8 | 27-Oct-2026 | 27-Oct-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
71 | Monitoring | Network Health Checks | Performance Detail | 8 | 28-Oct-2026 | 28-Oct-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
72 | Monitoring | Network Health Checks | Test Results | 8 | 29-Oct-2026 | 29-Oct-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
73 | Monitoring | Network Health Checks | [Buffer] Network Health Checks — bulk regression run & failure fix | 4 | 30-Oct-2026 | 30-Oct-2026 | Buffer | Reserved after all screens in submodule (total 3: 0 already done + 3 newly scheduled). Run suites in bulk, triage flakes/hard failures, refresh Allure, update workbooks.
74 | Monitoring | CSP & Tag Governance | Tag & Content Overview | 8 | 02-Nov-2026 | 02-Nov-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
75 | Monitoring | CSP & Tag Governance | Domain Details | 8 | 03-Nov-2026 | 03-Nov-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
76 | Monitoring | CSP & Tag Governance | Inventory Analysis | 8 | 04-Nov-2026 | 04-Nov-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
77 | Monitoring | CSP & Tag Governance | Domain Baseline Analysis | 8 | 05-Nov-2026 | 05-Nov-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
78 | Monitoring | CSP & Tag Governance | Service Profiles | 8 | 06-Nov-2026 | 06-Nov-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
79 | Monitoring | CSP & Tag Governance | Service Details | 8 | 09-Nov-2026 | 09-Nov-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
80 | Monitoring | CSP & Tag Governance | SLA Status | 8 | 10-Nov-2026 | 10-Nov-2026 | Planned | Playwright regression (POM) + Allure + manual workbook.
81 | Monitoring | CSP & Tag Governance | [Buffer] CSP & Tag Governance — bulk regression run & failure fix | 16 | 11-Nov-2026 | 12-Nov-2026 | Buffer | Reserved after all screens in submodule (total 7: 0 already done + 7 newly scheduled). Run suites in bulk, triage flakes/hard failures, refresh Allure, update workbooks.
82 | Account | Account Settings | My Account | 8 | 13-Nov-2026 | 13-Nov-2026 | Planned | View-only profile/account settings.
83 | Account | Account Settings | View Profile | 8 | 16-Nov-2026 | 16-Nov-2026 | Planned | View-only.
84 | Account | Account Settings | [Buffer] Account Settings — bulk regression run & failure fix | 4 | 17-Nov-2026 | 17-Nov-2026 | Buffer | Reserved after all screens in submodule (total 2: 0 already done + 2 newly scheduled). Run suites in bulk, triage flakes/hard failures, refresh Allure, update workbooks.

## Assumptions & Notes
Blue Triangle Portal — Automation Testing Plan (Assumptions & Notes)
Scope
• Screen inventory sourced from portal smoke catalog (config/smokeCatalog.ts), aligned to live portal.bluetriangle.com navigation labels.
• Core Web Vitals (VitalScope) under Improve Traffic covers the shared RUM performance-overview route; RUM VitalScope is not double-counted as a separate remaining screen.
• Automation is read-only regression (Playwright + TypeScript POM). No Save Filter, shared dashboard saves, create/edit/run write flows, or attribution config mutation.
Scheduling rules
• Completed screens listed first; historical dates assigned 22-Jul-2026 → 03-Aug-2026 at ~1 screen/day (matches delivery cadence).
• From 04-Aug-2026 onward: remaining Business Insights > Improve Traffic screens first, then Improve Conversion, Improve Revenue, then Monitoring (Advanced Reporting, Logs, Native, Synthetic, Network, Tag) and Account.
• Forward schedule uses business days (Mon–Fri). Weekends are non-working for projected dates.
• Standard Automation ETA = 8 hours per screen (analysis + POM/locators + regression suite + Allure + manual workbook).
Buffers
• After every submodule’s screens complete, a Buffer row is inserted for bulk suite execution and failure remediation.
• Buffer sizing (by full submodule screen count): ≤3 → 4h; 4–6 → 8h; 7–10 → 16h; 11+ → 24h.
• Partially completed submodules (Improve Traffic / Improve Conversion) size buffers on completed + remaining screens.
• Real User Browser historical buffer (16h) marked Completed — stabilization was absorbed during the Jul–Aug delivery window.
Status legend
• Completed (green) — suite delivered and executed.
• Planned (blue) — scheduled, not started.
• Buffer (orange) — reserved bulk-fix / stabilization slot (not a product screen).
• In Progress / Blocked — for live plan updates during execution.
Deliverables expected per screen
• Regression spec under tests/regression_tests/US2/…
• Page Object + Locators (reuse framework helpers)
• Isolated Allure HTML report
• Manual regression workbook (Summary / Regression TCs / Notes)
• npm script entry when applicable
Risks & leadership notes
• Live-data / site-dependent empty states may extend ETA on sparse environments; plan assumes GDC Test Site 2 has representative data.
• Sibling conversion-type screens (sales vs brand) are separate lines even when routes share a base path.
• Plan should be re-baselined if portal menu adds/removes leaves or if capacity changes (multiple engineers).
Generated: 03-Aug-2026 ¦ Regenerate: node scripts/generate-portal-automation-plan.js